## Sales
Task | SubTasks | Man Hours (Build)
OSC CPQ Integration | OSC setup | 40
| OIC setup | 40
| CPQ setup | 24
| User Provisioning | 16
| SSO\Oauth setups | 24
| Create New Quote | 16
| Edit New Quote | 16
| Clone Quote | 16
| Version Quote | 8
| Import Opportunity | 8
| Import Account | 8
| Import User | 8
| Sales Team | 20
| Return to Opportunity | 8
| Retun to Quote | 4
| Working with oracle operations team | 8
| Save Quote\Line | 40
| Mark Quote Active\Primary | 24
OSC Setup | Order Integration\Order Sync | 40
| Activity Integration | 32
| Document Attachments | 24
| Product Integration | 24
| Key Registration Information | 24

## OSvC Setup
Task | SubTasks | Man Hours (Build)
OSvC Web Version Upgrade |  | 40
OSvC Changes |  | 24
OSvC to CPQ Integration |  | 60
CPQ to OSvC Integration |  | 80

## SalesDriven
Flow Type | Pages | Application | Page Type | Integrated? | Number of Attributes (Range) | Application | Complexity | Man Hours (Builld) | Remark
Sales | Manage Opportunity Page | SalesCloud
Sales | Manage Sales Team | SalesCloud
Sales | Quotes Page | SalesCloud
Sales | Orders Page | SalesCloud
Sales | Activity Page | SalesCloud
Sales | ML.net Tracking | SalesCloud
Sales | Transaction Details | CPQ |  |  | 40 to 60 |  |  | 40 | Additional on top of order attributes
Sales | Customer Information | CPQ
Sales | Product Information | CPQ
Sales | Landing Screen | CPQ | [5 empty] | 24
Sales | Product Configuration | CPQ | [5 empty] | Included
Sales | Laser Engraving | CPQ
Sales | Pricing Details | CPQ
Sales:BidManagement | Approval Process | CPQ | [5 empty] | 80
Sales:BidManagement | Bid Management | CPQ | [5 empty] | 80

## Bid Management
Flow Type | Pages | Application | Page Type | Integrated? | Number of Attributes (Range) | Application | Complexity | Man Hours (Builld) | Remark
BidManagement | Transaction Details | CPQ |  | N
BidManagement | Approval Process | CPQ |  | N |  |  |  | 120
BidManagement | Bid Details\Maintenance | CPQ |  | N |  |  |  | 80
BidManagement | Bid Document | CPQ |  | N |  |  |  | 80

## ChannelPartners
Flow Type | Pages | Application | Page Type | Integrated? | Number of Attributes (Range) | Application | Complexity | Man Hours (Builld) | Remark
B2B | Transaction Details | CPQ |  | N |  |  |  | 40
B2B | Branding | CPQ |  | N |  |  |  | 120
B2B | Order Management |  |  | N |  |  |  | 80
B2B

## CSR_OE Driven
Flow Type | Pages | Page Type | Integrated? | Number of Attributes (Range) | Application | Complexity | Man Hours (Builld)
| CPQ Invocation |  |  |  | Service Cloud
| Transaction\Header Details (Others, Additional) |  |  | 35 to 50 | CPQ | Complex | 60
| Line Item Details |  |  | 40 to 60 | CPQ | Complex | 80
| Warranty Replacement |  |  |  | CPQ
| Account Search |  |  | 10 to 20 | CPQ
| Account Profile |  |  | 15 to 25 | CPQ
| Additional Details |  |  | Included | CPQ
| Notes & Attachments |  |  | 5 to 10 | CPQ
| Create and Update End User | Custom Page\Extensions (Non Transactional) | Y | 20 to 30 | CPQ | Medium | 24
| End User Registration | Custom Page\Extensions (Non Transactional) | Y | 10 to 20 | CPQ | Complex | 60
| View End User | Standard (Transactional) | Y | 15 to 25 | CPQ | Medium | 32
| View Combo Ranges | Custom Page\Extensions (Non Transactional) | Y | 10 to 15 | CPQ | Medium | 40
| View Combo Request | Custom Page\Extensions (Non Transactional) | Y | 30 to 40 | CPQ | Complex | 80
| View Comination Xref | Custom Page\Extensions (Non Transactional) | Y | 10 to 15 | CPQ | Medium | 60
| Enter Sub Lines | Standard\Extensions | N | 10 to 15 | CPQ | Low | 16
| Create\Update Ship To | Custom Page\Extensions (Non Transactional) | Y | 40 to 60 | CPQ | Complex | 120
| MFG Notes | Standard\Extensions | N | 15 to 20 | CPQ | Low | 16
? | Additional Order Details | Standard\Extensions | Y | 80 to 100 | CPQ | Complex | 140
? | Additional Order Lines | Standard\Extensions | Y | 120 to 140 | CPQ | Complex | 160
? | Apply Hold | Custom Page\Extension | Y | 5 to 10 | CPQ | Medium | 24
| Calculate Order Weight | Standard\Extension | Y | NA | CPQ | Medium | 16
| Expedite | Standard\Extensions | Y | 100 to 120 | CPQ | Complex | 160
Shipping Location Search
Shipping Location Maintenance
Connect to OSvC

## Common
Flow Type | Pages | Application | Page Type | Integrated? | Number of Attributes (Range) | Application | Complexity | Man Hours (Builld) | Remark
| Product Landing Screen | CPQ | [5 empty] | 80 | Direct Sales vs Channel Partner Setup
| Search Flow\Guided Selling | CPQ | [5 empty] | Done
| Item \ Mod Code Search | CPQ | Custom |  |  |  | Complex |  | Item\Mod Code Search, Cross Reference,
| Auto Configuration | CPQ | Extention |  |  |  |  | 120
| Product Configurations | CPQ | [5 empty] | Done
| Laser Engraving | CPQ | Custom |  |  |  |  | 120
| LIG\Product Information | CPQ | [5 empty] | 80
| Proposal Generation | CPQ |  |  |  |  | Medium | 200 | 80 for the first, 24 for every other. Considering 5 languages
| Handoffs | CPQ |  |  |  |  | Medium | 80 | Email Notification. 5 notification template
| Email Notifications | CPQ |  | N
| Reporting Manager | CPQ |  |  | 20 to 30 |  | Medium | 40
| Credit Card Processig | CPQ |  | Y | 5 to 10 |  | Medium | 80
| Troubleshooting | CPQ |  |  | 20 to 30 |  |  | 40
| User Setup | CPQ |  |  |  |  | Medium | 60 | Access Types, Groups, Security Permissions
| Process Setup | CPQ |  |  |  |  | Complex | 120 | Steps, profiles, transition rules, document views, access rights
| Multi-Currency | CPQ |  |  |  |  | Complex | 120
| Site Wide Navigations | CPQ |  |  |  |  | Medium | 40
| Parts Master Setup | CPQ |  | Y
| Pricebook Setup | CPQ |  | Y
| Pricing | CPQ |  |  |  |  | Complex | 120

## Other
Flow Type | Pages | Application | Page Type | Integrated? | Number of Attributes (Range) | Complexity | Man Hours (Builld) | Remark
| EDI Setup | CPQ |  | Y |  | Complex | 120 | Error Handing, Timer setups
| Order Integration | CPQ\OM |  | Y |  |  | 160 | Order Validations, Order Creations, Order Automation, Order Sync, Error Handling

## CSR Benefits
All regions including MLE will use the new system\platform
Guided search\product catalog search
Quick key line add (adding a configured item on a button click)
Copy Line Item
Copy and Version Quotes
Laser Engraving
Modern UI\UX
Multi lingual proposal templates: quote and order specific doc generation
One stop shop for all quotes\order tracking
Easy Handoff and collaborartion : quick turn around
Standard approval process for any internal reviews
Mobile Approval
Native reporting capability
Export\Import Line Items
Mass\Bulk upload features
User managed\data driven modelling
Mobile Enabled
Deal Analytics\Scatter plotting for executive deal desk