## Summary
Ref | Assumption/Comments
1 | Existing MLC order related coding will be leveraged wherever possible

## CPQ Estimates
Ref | Functional Area | Type | Process | Description | Related Tasks | Req | Design | Build | Unit Testing | QA | Hours | Weeks
1 | Sales Cloud - CPQ Integration |  | OSC Setup |  | * Site wide setups * Create\Edit\Clone\Version quote * Sales team setup | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | OIC Setup |  | * Setups\mappings | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | CPQ Setup |  | * Site wide settings * Import\Export XSL | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | SSO\User Provisioning |  | * SSO setups | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Sync Quote\Lines |  | * Mark quote active\quote\line syns | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Product Setup & Integration |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Order Sync\Integration:Reporting |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Activity Tracking |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Document Integration\Attachments |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | End User\Key Registration Information:Reporting |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Disable existing Bid Management Process |  |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
| Total | [9 empty] | 1232 | 30.8
13 | Service Cloud - CPQ Integration |  | Service Cloud Browser Version Upgrade |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | OSvC to CPQ Integration |  | * UI changes * Document attachment * Incident# tracking | 36 | 36 | 180 | 27 | 36 | 315 | 7.875
|  |  | CPQ to OSvC Integration |  | * Email Notifications * Document attachments | 36 | 36 | 180 | 27 | 36 | 315 | 7.875
18
19
| Total | [9 empty] | 700 | 17.5
21 | Product Catalog & Configuration |  | Setup Product Catalog |  | * Product Catalog * | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
22 |  |  | Guided Selling\Search Flow |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
23 |  |  | BOM Setup | All BOM setup |  | 84 | 84 | 420 | 63 | 84 | 735 | 18.375
24 |  |  | Configuration Attributes |  |  | 48 | 48 | 240 | 36 | 48 | 420 | 10.5
25 |  |  | BOM Mapping Rules |  |  | 128 | 128 | 640 | 96 | 128 | 1120 | 28
26 |  |  | Other advanced rules |  |  | 64 | 64 | 320 | 48 | 64 | 560 | 14
27 |  |  | UI\Configuration Flow |  |  | 38.4 | 38.4 | 192 | 28.8 | 38.4 | 336 | 8.4
28 | [5 empty] | 1.6 | 1.6 | 8 | 1.2 | 1.6 | 14 | 0.35
29 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
30 | [5 empty] | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
| Item Total | [9 empty] | 3458 | 86.45
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
Keying Total
53 | Order | API | EBS Order Processing | Wrapper package around Oracle Order API for order processing from CPQ to EBS | * Create order * Update order/lines * Cancel Order * Cancel line * Add Attachments * Add Notes * Add automated notes based on customer * Order updateable validation * Q2O, EDI, … * Apply Hold * Release Hold * Add Notes * Add Attachments * Book Order
54 | Order | Data Load | Order Entry Order Type | EBS order type list
55 | Order | Data Load | Payment Terms | EBS payment term list
56 | Order | Data Load | Sales Channel | EBS sales channel list
57 | Order | Data Load | Warehouse | EBS order line warehouse list (ship from org)
58 | Order | Data Load | Shipping Method | EBS order shipping methods available for header/line levels
59 | Order | Data Load | Freight Terms | EBS order freight terms available for header/line levels
60 | Order | Data Load | FOB | EBS FOB list
61 | Order | Data Load | Shipment Priority | EBS Shipment priorities available for order entry
62 | Order | Data Load | Tax Handling | EBS taxing options
63 | Order | Data Load | Exempt Reason | EBS tax exemption reasons
64 | Order | Data Load | Payment Type | EBS payment type list (Default, Check, Credit Cart…)
65 | Order | Data Load | Credit Card Brand | EBS credit card types
66 | Order | Data Load | Final Destination Ctry | EBS A1 DFF attribute list of values
67 | Order | Data Load | Order Brokered | EBS A1 DFF attribute list of values
68 | Order | Data Load | Freight Allowance | EBS A1 DFF attribute list of values
69 | Order | Data Load | Third Party Freight Account | EBS A1 DFF attribute list of values
70 | Order | Data Load | Rounding Rule | EBS A1 DFF attribute list of values
71 | Order | Data Load | Back Order Policy | EBS A1 DFF attribute list of values
72 | Order | Data Load | Account Of | EBS A1 DFF attribute list of values
73 | Order | Integration | Order Header Sync | Sync order header updates from EBS to CPQ
74 | Order | Integration | Order Line Sync | Sync order line updates from EBS to CPQ
75 | Order | Service | Line Set | Order line level "Line Set" option list | Oracle standard LOV option
76 | Order | Service | Get Item Availability Date | Returns date for order line value
77 | Order | Service | Get Set Availability Date | Calculates and returns order line Item Available Date
78 | Order | Service | Set ship sets | Determines ship sets at order line level. Part of custom booking process.
79 | Order | Service | Sales Rep Search | Sales Rep list of values
80 | Order | Service | Additional Order Information | Display order header information (standard functionality) | Tabs * Holds * Deliveries * Invoices/Credit Memos * Quantity History
81 | Order | Service | Additional Line Information | Display order lined information (standard functionality) | Tabs * Holds * Returns * Deliveries * Invoices/Credit Memos * Internal Requisition * Drop Ship * Quantity History
82 | Order | Service | Expedite | Custom information request displaying various line item details (complex) | Tabs * Call Center * Additional Info * Manufacturing * VAM * Inventory/Purchasing * Shipping * Addresses
83 | Order | Service | Calculate Order Weight | Custom calculation of order weight
84 | Order | Service | View Adjustments (Header) | View adjustments applied at order header level; Adjustment, Reason tabs
85 | Order | Service | View Adjustments (Line) | View adjustments applied at order line level; Adjustment, Reason tabs
86 | Order | Service | View Charges (Line) | View charges applied to order line level
87 | Order | Service | Get Default Sales Rep | Derives default sales rep populated on order header
88 | Order | Service | Get Sales Channel | Get default sales channel based on order type
89 | Order | Service | Get Ship To Attributes | Get DFF values based on ship to
90 | Order | Service | Get Standard Order Information | Standard items populated by Oracle during order creation
91 | Order | Service | Duplicate Order Check | Checks if order is duplicate base on customer, ship to, attribute13 and date range | Not sure if this will apply to CPQ
92 | Order | Service | Customer Pre-Set Notes | Automated notes added to order based on customer | This should be handled in CPQ
93 | Order | Service | Set Line Attributes | Enables and disables order line fields based on item, item type, item attributes | This should be handled in CPQ
94 | Order | Service | Validate Set Size | Validation of quantity ordered set value
95 | Order | Service | Validate Order Quantity | Validates ordered quantity against customer rounding code and item attributes
96 | Order | Service | Copy Attribute Field | Updates order line attribute field with new value if different | Not sure if this will apply to CPQ
97 | Order | Service | Validate Order Line | Validates if customer item cross reference is needed and available
98 | Order | Service | Set Request Date | Calculates Request Date, Promise Date and Schedule Ship Date on order line
99 | Order | Service | MLC Insert Update Validate | Calls Validate Line, verifies ship set values
100 | Order | Service | Validate Line | Verifies is all required data has been defined on the order line
101 | Order | Service | Get Config Description | Used to populate the item description on order line from configurator | This should be handled in CPQ
102 | Order | Service | Copy Ordered Quantity | Copies ordered quantity to set size.
103 | Order | Service | Copy MLC Display Fields | Copies order line values to order line DFF fields.
104 | Order | Trigger | Order Header | OE_ORDER_HEADERS
105 | Order | Trigger | Order Line | OE_ORDER_LINES
| Order Total | [9 empty] | 0 | 0
107 | Pricing | API | Price Request | Wrapper package around Oracle Price Request API | * Calculate Price * Calculate Freight * Calculate Tax ?
108 | Pricing | Data Load | Oracle Price Lists | EBS price list integration to CPQ
109 | Pricing | Data Load | Promotions List | EBS promotion list integration to CPQ
110 | Pricing | Data Load | Currency | EBS order/price list currency and currency code values
111 | Pricing | Data Load | Price Override Users | Users with access to override prices based on EBS profile
112 | Pricing | Integration | Price Promotions Sync | Sync promotion updates from EBS to CPQ
113 | Pricing | Integration | Price Override Users | Sync users with pricing override access to CPQ
114 | Pricing | Integraton | Price List Sync | Sync price list updates from EBS to CPQ
115 | Pricing | Service | View Tax Details | View taxes applied at order line level
116 | Pricing | Service | Get Standard Price List | Function to return standard price list for customers not assigned to standard price list
117 | Pricing | Trigger | Price Lists | QP_LIST_HEADERS
118 | Pricing | Trigger | Promotions | QP_MODIFIERS
119 | Pricing | Trigger | Price Override Users | FND_PROFILE_OPTIONS
| Pricing Total | [9 empty] | 0 | 0
| Grand Total | [9 empty] | 5390 | 134.75
[9 empty] | Developers | Months
[9 empty] | 3 | 11.2292
Months by Functional Area
[9 empty] | Account | 7.7
[9 empty] | End User | 4.375
[9 empty] | Item | 21.6125
[9 empty] | Keying | 0
[9 empty] | Order | 0
[9 empty] | Pricing | 0
[9 empty] | Total | 33.6875