## Summary
Ref | Assumption/Comments
1 | Existing MLC order related coding will be leveraged wherever possible

## CPQ Estimates
Ref | Functional Area | Type | Process | Description | Related Tasks | Req | Design | Build | Unit Testing | QA | Hours | Weeks
1 | Sales Cloud - CPQ Integration |  | OSC Setup | Initial setups which needs to be done from OSC in order to configure CPQ integration. This includes Customizations, Configurations and other setups. | * Site wide setups * Page Layouts * Create\Edit\Clone\Version Actions on quote * Sales team setup * Validations and Rules | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | OIC Setup | Setting OIC application to help systems in back and froth data and users flow. This includes managing adapters, application mappings, data triggers, etc. | * Adapter and Connections * Setup/Mappings * Triggers | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | CPQ Setup | Complete Initial setup, vendor level standard settings, managing Integrations and other setups to help CPQ in builing connections with upstream and downstream applications | * Initial setup * Site wide settings * Import\Export XSL | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | SSO\User Provisioning | User can access Sales cloud to CPQ and vice versa without login again, using SAML authentication. Setting IdP and SP and using middleware for seamless connection between applications. | * SSO setups * Validations * User Import | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Sync Quote\Lines | Complete setup of Quotes and lines sync between OSC and CPQ applications. This helps in creation and update of revenue lines on Opportunity. | * Mark quote active\quote\line sync * Import\Export XSL | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Product Setup & Integration | Creation of Models with all setups and Integrate to OSC | * Setup and Configrations * Part Integration | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Order Sync\Integration:Reporting | 360 view for Order in Sales Cloud application and keep all related data in sync with EBS and CPQ applications. | * Order initial setups * Page Layouts and subtabs * Orders related data sync * Reporting | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Activity Tracking | Logging follow up activities and tasks performed within CPQ in the Sales Cloud Opportunity | * Integration and Actions setup * Mappings | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Document Integration\Attachments | Importing Attachmnets over on Sales Cloud from CPQ. Attachments will be proposals, Bid Documents, etc. | * Import Attachment * Export Attachment | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | End User\Key Registration Information:Reporting | Key registration and End User related data back and froth data sync and later using this info in Sales cloud for reporting. | * Account Integration * Key registration related fields setup * Reporting | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Disable existing Bid Management Process | As process is moving to CPQ, existing process in Sales cloud need to be removed | * Disabling Worflows and Notifications * Page layout changes * Removing validations and triggers | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
[11 empty] | 1232 | 30.8
13 | Service Cloud - CPQ Integration |  | Service Cloud Browser Version Upgrade | Users can use Service cloud without any instalations, directly from Browser using link | *Desktop to Browser upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | OSvC to CPQ Integration | Navigation from Service cloud to CPQ cloud and consume Quote process | * UI changes * Document attachment * Incident# tracking | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | CPQ to OSvC Integration | Attaching proposals to the Service cloud's Incident Attachment and sending incident response to the customer contact's mail | * Email Notifications * Document attachments | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
[11 empty] | 420 | 10.5
17 | Product Catalog & Configuration |  | Setup Product Catalog | Creation of Product family and its heirachy along with configuration setup | * Product Catalog & Heirarchy * Model Configuration Setups | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
18 |  |  | Guided Selling\Search Flow | Guided selling uses technology to automate the sales process, allowing your sales teams to focus on the right customers and helping your customers easily find and configure the right products and services. | *Search Parameter Defntions *Selector flow | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
19 |  |  | BOM Setup | The BOM Item Definition Table stores the BOM hierarchical relationships used in the fulfillment system, along with item variable references, which recursively link child items to parent items. In addition to the hierarchical information, it also stores other information from the fulfillment BOM, such as: Fulfillment system IDs Default quantity Whether an item is optional, a sales item, or a manufacturing item BOM item effective dates | *BOM Item Definition setup(24) | 111 | 111 | 555 | 83.25 | 111 | 971.25 | 24.2812
24 |  |  | Configuration Attributes | Configurable attributes define the characteristics of product families | *Attribute Definitions *Default Rules | 60 | 60 | 300 | 45 | 60 | 525 | 13.125
21 |  |  | BOM Mapping Rules | The BOM Item Mapping table associates BOM items to Configuration attributes. Activating this table enables simple Table-Based BOM Mapping Configuration rules. | *BOM Item Mapping Rules (24) | 163.6 | 163.6 | 818 | 122.7 | 163.6 | 1431.5 | 35.7875
22 |  |  | Other advanced rules | Functionalities which we can't achieve through standard rules in such case will go for advanced rules like BML based Rules | *Other adanced BOM mapping *BML extensions | 76.4 | 76.4 | 382 | 57.3 | 76.4 | 668.5 | 16.7125
23 |  |  | UI\Configuration Flow | User Interface | *Configuration Flow | 32.8 | 32.8 | 164 | 24.6 | 32.8 | 287 | 7.175
[11 empty] | 4233.25 | 105.8312
25 | General Setup |  | Product Landing Screen | Home Page setup and Providing/Restricting Model access to the customers based on their requirements. | *Direct Sales Access, Channel Partner Access | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Customer & Account Setup | It typically stores the customer details like name,Id,shipping or billing address and so..on | * Import Accounts | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
27 |  |  | Item \ Mod Code Search | Custom search page | * Custom Item Search | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
28 |  |  | Auto Configuration | In Configuration Page, it refresh/updates the model without click on update action | * Auto updates | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
29 |  |  | Laser Engraving | Ability to include visuals in customer documents - this feature would be helpful to show the customer what the lock would look like with features like laser engravings. | *Laser Engraving | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
30 |  |  | LIG\Product Information | It represents the data in a hierachical way which consists of ATO Models,Option classes and parts | *Display BOM * Display Actions | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
31 |  |  | Proposal Generation | It generates the proposal document of all required details | *Generation of Proposal Document | 36 | 36 | 180 | 27 | 36 | 315 | 7.875
32 |  |  | Handoffs | Streamline multiple hand-offs for approval with automated workflow | * Approval Handoffs | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
33 |  |  | Email Notifications | Email Notifications for approval with automated flow | * Approval Email Notifications | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
34 |  |  | Reporting Manager | A Reporting Manager is available for every Commerce Process in the system. Users can store, edit, run and manage reports in the Report Manager. | * Reports | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
35 |  |  | Credit Card Processig | Process the customer payments through credit cards | * Payments | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
36 |  |  | User Setup | Users can be created in the host company | *Import Users | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
37 |  |  | Process Setup | In process we will define B2B sales process and will implement required setup | *Steps,Profiles,Transiton Rules *Document Views, Access Rights | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
38 |  |  | Multi-Currency | It involves or uses more than a currency | * Exchange Rates, Conversions | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
39 |  |  | Site Wide Navigations | Access the desired areas using the side/top navigation menus.What appears in these menus can be customized based upon where the page you, or the user, happen to be working on: Admin, Commerce, Quick Registration, Subheader and Subfooter. | *Navigation Menus | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
40 |  |  | Parts Master Setup | Imports the parts through integration and sync the parts | *Parts Setup/Integartion of Parts | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
41 |  |  | Pricebook Setup | Imports the pricebook through integration and sync the price books | *PriceBook Setup/Integartion of PriceBook | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
42 |  |  | Pricing Setup | All the scenarios including Price quote\order\lines | *Pricing setup *Integration Setup | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
[11 empty] | 2835 | 70.875
| Bid Management |  | Bid Details | Before final Approvals, all the Bid related details to be required on transaction, once user opts for Bid/Discount | *Bid Details eg Bid#, Expiry, | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Bid Management Approval Process | Approvals to get Bids or Discounts. Approvers will receive notification for approvals. | * Product details, pricing exceptions\Discounts, Routings * Approval Email Notifications | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Bid Administration Maintenance | Bids usage and other related details calculations | * Consumtion, Expiry extensions | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Bid Document Management | Management of Bid Documents throughout the Bid lifecycle which includes Document/Proposal generation, User's Acceptance and lastly on submitting for Order it moves to Awarding. | * Bid Document Generation, Acceptance, Awarding | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
[11 empty] | 385 | 9.625
| Channel Partner |  | Transaction Details | In transaction details will create the attributes,actions and provides the document views | *Setups, Document Views | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Styling & Branding | Customize the instance through CSS | * Custom CSS | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | User Setups | Users will be created to acccess the Oracle CPQ and Perform the actions of Create/Update/Delete/Modify in the instance | *Create/Edit transaction *Book the Order | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Internal Approval & Handoffs | An Approval process is mandatory for every business that wants to be successful. It helps to maintain high service standards, stay on track with time and finances and helps to ensure everyone is on the same page | * Approval Process | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Document Generation | Documentation gives you sales reps accurate information they can share quickly or happens more quickly | * Order Summary/Product Details | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
[11 empty] | 490 | 12.25
| OE\Speciality Service Activities |  | Manage Keying | Pages required for manageing Keying and related content (included with config estimates) | *Manage Patented Keyway Manage MasterKey *Manage\Validate KeyChange | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Transaction\Header Details (Main,Others, Additional) | In transaction\Header details will define the attributes, get the bill to ship to details and provide the rules based on their requirements and so..on | *Defaulting Rules *Customer lookup *Order Lookup | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Line Details | Provide the details with part name and its quantity,description, price,discount,part type etc.., | *Import Line Items * Export Line Items *Unit Price | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Notes & Attachments | Integrate the manufacturing notes/Attachments to EBS | *Manufacture Notes *Proposal | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  |  | End User Maintenance | Custom pages required around End user maintenance | *Create and update end user *End Uer Registration *View End User | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | Mange Combo Ranges\Request |  | *View Combo Ranges *View Combo Request *View Comination Xref | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | Enter Sub Lines | Used for Product Sets, Locker Lock, List Orders to enter Serial # or Key Change by order line | *View Subline Information *Capture Subline Information | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Ship To Maintenance | Custom pages required around End user maintenance | *Create and Update Ship To Details *Create/Modify Address *View Shipping / Billing Address *View Delivery Address | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | MFG Notes | Capture notes for manufacturing | *Form needed to capture the notes | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Additional Order Details | Additional Order Level Details required for Information only | *Display values related to Hold *Display values related to Deliveries\Delivery Details *Display details on Invoices\Credit Memos | 28 | 28 | 140 | 21 | 28 | 245 | 6.125
|  |  | Additional Line Details | Additional Line Level Details required for Information only | *Display values related to Hold *Display values related to Deliveries\Delivery Details *Display details on Invoices\Credit Memos | 32 | 32 | 160 | 24 | 32 | 280 | 7
|  |  | Calculate Item Weight | Calculate item weight of configured items (components) | Included with integration setup | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Apply Hold | Custom form for applying hold in Order Management | *Display form to capture fields required | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  |  | Calculate Order Weight | Custom calculation of order weight | *Identify parameters used for the integration call *Action\tab required for user selection | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Cancel Header | Page required to cancel order\all lines | *Create Form Pages (3) *Apply Validations *Define Criteria | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Cancel Line | Page required to cancel individual line | *Create Form Pages (1) *Apply Validations *Define Criteria | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  |  | Expedite | Forms mostly used by CSR team | *Header Details *Call Center Detaills *Manufacturing Details *Additional Details *VAM Details *Inventory\Purchasimng Details *Shipping Details *Address Details etc | 32 | 32 | 160 | 24 | 32 | 280 | 7
|  |  | Price Order\Line | Included with common functionality |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Charges | Pages required to get the details on the charges | *Create Form Pages (5) *Apply Validations *Define Criteria | 20 | 20 | 100 | 15 | 20 | 175 | 4.375
|  |  | View Tax Details | Assumption : tax integration is part of EBS pricing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Manage Promotions at Header\Line Level | Pages required to manage promitions in CPQ | *Create Promotions Related Pages *Apply Promotions | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Release Holds | Pages required to release hold functionality | *Create Form Pages (5) *Define Criteria | 7.2 | 7.2 | 36 | 5.4 | 7.2 | 63 | 1.575
|  |  | View Adjustments (Header\Line) | Pages required to view adjustments in OM | *Create View Adjustment Pages (5) | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | Item Supply Demand | Pages required to check Item Supply Demand | *Item Supply demand Form Pages (1) | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Item On Hand | Custom form built on On-hand Quantities. Results will be for all warehouses | *Item On Hand CustomPages (5) | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Line Set | Manage Line Set\Groupting |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  |  | All other Keying Activities | Setups required to manage various keying activities | *Assign ADA Master Key *Assign Door Key *Assign Next ADA Bind Code/Serial *Assign\validate Serial Number *Check Serial Quantity *Get Existing Control Key *Validate ADA Serial Number *Validate Customer Key Numbers *Validate Edge Virtual Keyways *Validate Key Master *Validate System | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sales Order Processing |  | *Creat Sales Order *Update Sales Order *Change Order | 32 | 32 | 160 | 24 | 32 | 280 | 7
|  |  | Validate Order\Order Lines |  | *Validate End User *Order Quantity *Set Size *Master Key | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
[11 empty] | 3304 | 67.025
| Integration Impact |  | Manage End User Related Integration Setups | End user data create/update | *End User Create/Maintain *End User View *End User Notes *End User Registration\Details *Validate End User *End User Sync | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Combo Ranges\Request Related Integration Setups | View serial number to find serial number range | *View Serial Number *Combo Ranges *Combo Request | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Laser Engraving | Enter text details for manufacturer laser instructions
|  | Not Needed | Mfg Notes | Notes to manufacturer | Included | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Not Needed | Sub Lines | Used for Product Sets, Locker Lock, List Orders to enter Serial # or Key Change by order line | Included
|  |  | Manage Ship To related Integration Setup |  | *Create and Update Ship To Details *Create/Modify Address *View Shipping / Billing Address *View Delivery Address | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Item | Item LOV | *Custom Item Search Page | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Synchronize Parts\Products | Synchronize the EBS PIM Products and BOM information with CPQ | *Scedules part\producst integration setup *One time conversion\parts setup *Sales Cloud Parts | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Synchronize BOMs | Synchronize the EBS PIM Products information with Sales Cloud | *FTP automation | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Order Details view | Order details view
|  | Data Load\Conversion | Parts Information | Part Conversion: Sync existing and new item\parts | *One time load
|  |  | PriceBook | PriceBook
|  |  | EDI Orders | This integration process includes quote creation, adding product, other required quoting option, validations and order processing |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Customer Lookup | Get Customer Details | Included above | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Quote\Line Item Sync | Upsert Quote\Line Item attributes | Included above | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Export Attachment | Export quote related documents\attachments | Included above | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Import Attachment | Import quote related documents\attachments | Included above | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Quote\Line to Opportunity\Revenue Lines Sync | Synch primary quote\line details to Opportunity\Revenue Lines Sync
|  |  | TAX Integration | Process required to calcuate TAX for finance team | Part of EBS pricing | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Credit Card Processing | Process required to capture Credit Card details | Included above | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Service | Item Availability | Item/Warehouse Availibility. ML has functionality. Plan is to replicate for CPQ call. |  | 7.2 | 7.2 | 36 | 5.4 | 7.2 | 63 | 1.575
|  | Service | Address Infomarion | Bill To/Ship To/Deliver To Address. Return address type by Account Id
|  | Service | Sales Order Details | Sales order additional information | Included above | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | API | Create EBS Order | Quote to Order API for converting CPQ quote to order
|  | API | Update EBS Order | Order update initiated from CPQ. Updates will depend on matrix
|  | API | Cancel EBS Order\Order Lines Setups | Order cancellation API executed from CPQ |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  | API | BOM Exists | Checks if inbound configuration from CPQ exists as BOM in EBS
|  | API | Create BOM | Creates BOM in EBS from inbound CPQ configuration
|  | Service | Copy End User ID | Copies line end user to line attribute
|  | Service | Validate End User | End user validation call |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  | Service | Item Supply/Demand | Returns item supply and demand for an item in all orgs |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  | Service | Item On Hand Quantity | Returns onhand quantity for item in all orgs |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  |  | Item Cross Reference | Sync EBS customer cross reference updates |  | 2.4 | 2.4 | 12 | 1.8 | 2.4 | 21 | 0.525
|  | Service | Calculate Item Weight | Calculate iem weight of configured items (components) |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  | Service | Load item attributes | Fetches and sets various item attributes on order line. Based on SKU selected, function returns values related to item and pre-populates fields on order line needed for validation. |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  | Service | Get ATO flag | Derives if item is ATO item or stock item
|  | Transaction | Update Item Weight | Update MLC UOM cross reference item data
|  | Service | Assign Serial Number | Gets next available serial number for a model |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Validate Key Master | Master validation entered on order line or in configuration |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Validate Serial Number | Combination key serial number validation |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  |  | Validate Edge Virtual Keyways | Validation of edge keyways, key level and customer class of trade for product |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  |  | Validate Customer Key Numbers | Validate key numbers associated with customer |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Validate Control Key | Validates control key for model |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Get Existing Control Key | Gets list of control keys used by end user |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Validate ADA Serial Number | Validates serial number for ADA lock |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Assign ADA Master Key | Query to determine available master key for ADA locker locks |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Get Next ADA Bind Code/Serial | Reviews registration to return next blind code/serial for ADA lock |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Get KD Begin Master Key | Retrieve beginning key for KD order |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Check Serial Quantity | Checks key serial quantity against ordered quantity |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Validate System | Validates key configuration - item, key range Id, end user… |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Assign Door Key | Assigns master and change key for residential door hardware |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Integration | Order Header Sync | Sync order header updates from EBS to CPQ |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  | Integration | Order Line Sync | Sync order line updates from EBS to CPQ |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  | Service | Line Set | Order line level "Line Set" option list |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  | Service | Get Item Availability Date | Returns date for order line value
|  | Service | Get Set Availability Date | Calculates and returns order line Item Available Date
|  | Service | Set ship sets | Determines ship sets at order line level. Part of custom booking process.
|  | Service | Sales Rep Search | Sales Rep list of values
|  | Service | Additional Order \Lne Information related setup | Display order header information (standard functionality) |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  | Service | Expedite | Custom information request displaying various line item details (complex) |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  | Service | Calculate Order Weight | Custom calculation of order weight |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | View Adjustments Header\Line Integration Setups | View adjustments applied at order header level; Adjustment, Reason tabs |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  | Service | View Charges (Line) Integration Setup | View charges applied to order line level | *Prepare Payload\Parameters *Validate and Parse response *Error Handling | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  | Service | Get Default Sales Rep | Derives default sales rep populated on order header
|  | Service | Get Sales Channel | Get default sales channel based on order type
|  | Service | Get Ship To Attributes | Get DFF values based on ship to
|  | Service | Get Standard Order Information | Standard items populated by Oracle during order creation
|  | Service | Duplicate Order Check | Checks if order is duplicate base on customer, ship to, attribute13 and date range |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Customer Pre-Set Notes | Automated notes added to order based on customer
|  | Service | Set Line Attributes | Enables and disables order line fields based on item, item type, item attributes
|  | Service | Validate Set Size | Validation of quantity ordered set value |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Validate Order Quantity | Validates ordered quantity against customer rounding code and item attributes |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | Copy Attribute Field | Updates order line attriubute field with new value if different
|  | Service | Validate Order Line | Validates if customer item cross reference is needed and available |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Service | Set Request Date | Calculates Request Date, Promise Date and Schedule Ship Date on order line |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  | Service | MLC Insert Update Valiate | Calls Validate Line, verifies ship set values
|  | Service | Validate Line | Verifies is all required data has been defined on the order line |  | 4 | 4 | 20 | 3 | 4 | 35 | 0.875
|  | API | Price Request Integration Setup | Wrapper package around Oracle Price Request API |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Data Load | Oracle Price Lists | EBS price list integration to CPQ
|  | Data Load | Promotions List | EBS promotion list integration to CPQ
|  | Data Load | Price Override Users | Users with access to override prices based on EBS profile
|  | Integration | Price Promotions Sync | Sync promotion updates from EBS to CPQ |  | 2.4 | 2.4 | 12 | 1.8 | 2.4 | 21 | 0.525
|  | Integration | Price Override Users | Sync users with pricing override access to CPQ
|  | Integraton | Price List Sync | Sync price list updates from EBS to CPQ (Included) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Service | View Tax Details | View taxes applied at order line level (Part of EBS pricing. Not included in CPQ estimates) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data Loads | Data loads | All other data loads throughout commerce & configuration | General Data Loads | *Account of *Back Order Policy *Card Brand *Currency *ExemptReason *Final Destination *FOB *Freight Allowance *Freight Terms *Order Type *Payment Terms *Sales Channel *Shipping Priority *Shipping Method *Tax Handlinf *Warehouse *Price Override Users *Promotions List etc | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
[11 empty] | 2534 | 63.35
[11 empty] | 0 | 0
| Other Activities |  | Cut Over & Migration |  |  | 4 | 4 | 20 | 3 | 4 | 35 | 0.875
|  |  | SIT |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | UAT |  |  | 4 | 4 | 20 | 3 | 4 | 35 | 0.875
|  |  | Change Mangement |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | PMO |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | HyperCare |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Detailed Technical Documentation |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Knowledge Transfer |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
[11 empty] | 805 | 20.125
| Grand Total | [9 empty] | 16238.25 | 405.9562
[9 empty] | Developers | Months
[9 empty] | 5 | 20.2978
Months by Functional Area
[9 empty] | Sales Cloud - CPQ Integration | 7.7
[9 empty] | Service Cloud - CPQ Integration | 2.625
[9 empty] | Product Catalog & Configuration | 26.4578
[9 empty] | General Setup | 17.7188
[9 empty] | Bid Management | #REF!
[9 empty] | Channel Partner | 0
OE Activities
Integration Impact
[9 empty] | Total | #REF!

## High Level Scope Activities
Phase1 | Phase2 | Phase3
OSC-CPQ Integration | OSvC-CPQ Integratio | Channel Partner Organization Setup
User Setup | User Setup
CPQ Process Setup | OE activities
Define Product Catalogs | Additional CSR Activities
Guided Selling | Auto Configuration Setup
Item\Mod Code Search | Document Generation
BOM\Rules Setup | Order Processing
Product Configurations | Order Sync
Pricing Setups | Warranty Replacement Orders
Document & Proposal Generation | EDI Order Processing
Onboard Global SalesUsers to Sales Cloud | Order Integrations for Sales
Laser Engraving | Onboard Global Service Users to Service Cloud
Forecasting & Reporting
Handoff
Bid Management

## Out Of Scope
Out of Scope Item (ML Owned)
Service Cloud Browser Setup
ML.net UPS tracking
Global User : Sales Process Enablement
Global User : Service Process Enablement
BOM re-engineering
Config Rules Validations
Star Item Creation
PitneyBows Document Generation
Commercial Invoicing
Any other downstream impact post booking
Dan's Speciality Service Activities