## Summary
Ref | Assumption/Comments
1 | Existing MLC order related coding will be leveraged wherever possible

## CPQ Estimates
Ref | Functional Area | Type | Process | Description | Related Tasks | Req | Design | Build | Unit Testing | QA | Hours | Weeks
1 | Sales Cloud - CPQ Integration |  | OSC Setup |  | * Site wide setups * Create\Edit\Clone\Version quote * Sales team setup | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | OIC Setup |  | * Setups\mappings | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | CPQ Setup |  | * Site wide settings * Import\Export XSL | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | SSO\User Provisioning |  | * SSO setups | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Sync Quote\Lines |  | * Mark quote active\quote\line syns | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Product Setup & Integration |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Order Sync\Integration:Reporting |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Activity Tracking |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Document Integration\Attachments |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | End User\Key Registration Information:Reporting |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Disable existing Bid Management Process |  |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
[11 empty] | 1232 | 30.8
13 | Service Cloud - CPQ Integration |  | Service Cloud Browser Version Upgrade |  | *Desktop to Browser upgrade | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | OSvC to CPQ Integration |  | * UI changes * Document attachment * Incident# tracking | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | CPQ to OSvC Integration |  | * Email Notifications * Document attachments | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
[11 empty] | 560 | 14
17 | Product Catalog & Configuration |  | Setup Product Catalog |  | * Product Catalog & Heirarchy * Model Configuration Setups | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
18 |  |  | Guided Selling\Search Flow |  | *Search Parameter Defntions *Selector flow | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
19 |  |  | BOM Setup |  | *BOM Item Definition setup(24) | 111 | 111 | 555 | 83.25 | 111 | 971.25 | 24.2812
24 |  |  | Configuration Attributes |  | *Attribute Definitions *Default Rules | 60 | 60 | 300 | 45 | 60 | 525 | 13.125
21 |  |  | BOM Mapping Rules |  | *BOM Item Mapping Rules (24) | 163.6 | 163.6 | 818 | 122.7 | 163.6 | 1431.5 | 35.7875
22 |  |  | Other advanced rules |  | *Other adanced BOM mapping *BML extensions | 76.4 | 76.4 | 382 | 57.3 | 76.4 | 668.5 | 16.7125
23 |  |  | UI\Configuration Flow |  | *Configuration Flow | 32.8 | 32.8 | 164 | 24.6 | 32.8 | 287 | 7.175
[11 empty] | 4303.25 | 107.5812
25 | General Setup |  | Product Landing Screen |  | *Direct Sales Access, Channel Partner Access | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Customer & Account Setup |  |  | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
27 |  |  | Item \ Mod Code Search | Custom search page |  | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
28 |  |  | Auto Configuration |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
29 |  |  | Laser Engraving |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
30 |  |  | LIG\Product Information |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
31 |  |  | Proposal Generation |  |  | 36 | 36 | 180 | 27 | 36 | 315 | 7.875
32 |  |  | Handoffs |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
33 |  |  | Email Notifications |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
34 |  |  | Reporting Manager |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
35 |  |  | Credit Card Processig |  |  | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
36 |  |  | User Setup |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
37 |  |  | Process Setup |  | *Steps,Profiles,Transiton Rules *Document Views, Access Rights | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
38 |  |  | Multi-Currency |  | * Exchange Rates, Conversions | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
39 |  |  | Site Wide Navigations |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
40 |  |  | Parts Master Setup |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
41 |  |  | Pricebook Setup |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
42 |  |  | Pricing Setup | All the scenarios including Price quote\order\lines |  | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
[11 empty] | 2730 | 68.25
| Bid Management |  | Bid Details |  | *Bid Details eg Bid#, Expiry, | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Bid Management Approval Process |  | *Product details, pricing exceptions\Discounts, Routings | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Bid Administration Maintenance |  | * Consumtion, Expiry extensions | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Bid Document Management |  | * Bid Document Generation, Acceptance, Awarding | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
[11 empty] | 385 | 9.625
| Channel Partner |  | Transaction Details |  | *Setups, Document Views | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Styling & Branding |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | User Setups |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Internal Approval & Handoffs |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Document Generation |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
[11 empty] | 490 | 12.25
| OE\Speciality Service Activities |  | Transaction\Header Details (Main,Others, Additional) |  | *Defaulting Rules *Customer lookup *Order Lookup | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Line Details |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Notes & Attachments |  |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  |  | End User Maintenance | Custom pages required around End user maintenance | *Create and update end user *End Uer Registration *View End User | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | Mange Combo Ranges\Request |  | *View Combo Ranges *View Combo Request *View Comination Xref | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
Enter Sub Lines
|  |  | Ship To Maintenance | Custom pages required around End user maintenance | *Create and Update Ship To Details *Create/Modify Address *View Shipping / Billing Address *View Delivery Address | 24 | 24 | 120 | 18 | 24 | 210 | 5.25
|  |  | MFG Notes | Capture motes for manufacturing | *Form needed to capture the notes | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Additional Order Details | Additional Order Level Details reuired for Information only | *Display values related to Hold *Display values related to Deliveries\Delivery Details *Display details on Invoices\Credit Memos | 32 | 32 | 160 | 24 | 32 | 280 | 7
|  |  | Additional Line Details | Additional Line Level Details reuired for Information only | *Display values related to Hold *Display values related to Deliveries\Delivery Details *Display details on Invoices\Credit Memos | 32 | 32 | 160 | 24 | 32 | 280 | 7
|  |  | Apply Hold--------Need to find integration details | Custom form for applying hold in Order Management | *Display form to capture fields required | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  |  | Calculate Order Weight | Custom calculation of order weight | *Identify parameters used for the integration call *Action\tab required for user selection | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | Cancel Header | Page required to cancel order\all lines | *Create Form Pages (3) *Apply Validations *Define Criteria | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Cancel Line | Page required to cancel individual line | *Create Form Pages (1) *Apply Validations *Define Criteria | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
Copy Order???? Need to discuss with Pat
|  |  | Expedite | Forms mostly used by CSR team | *Header Details *Call Center Detaills *Manufacturing Details *Additional Details *VAM Details *Inventory\Purchasimng Details *Shipping Details *Address Details etc | 32 | 32 | 160 | 24 | 32 | 280 | 7
|  |  | Price Order\Line | Included with common functionality |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Charges | Pages required to get the details on the charges | *Create Form Pages (5) *Apply Validations *Define Criteria | 20 | 20 | 100 | 15 | 20 | 175 | 4.375
View Tax Details???Need to check with Pat
|  |  | Manage Promotions at Header\Line Level….still working | Pages required to manage promitions in CPQ | *Create Promotions Related Pages *Apply Promotions | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Release Holds--------Need to find integration details | Pages required to release hold functionality | *Create Form Pages (5) *Define Criteria | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | View Adjustments (Header\Line) | Pages required to view adjustments in OM | *Create Form Pages
[11 empty] | 2513 | 62.825
| Integration Impact |  | Manage End User Related Integration Setups | End user data create/update | *End User Create/Maintain *End User View *End User Notes *End User Registration\Details | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  |  | Combo Ranges\Request Related Integration Setups | View serial number to find serial number range | *View Serial Number *Combo Ranges *Combo Request | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  | ? | Laser Engraving | Enter text details for manufacturer laser instructions
|  | Not Needed | Mfg Notes | Notes to manufacturer
|  | Not Needed | Sub Lines | Used for Product Sets, Locker Lock, List Orders to enter Serial # or Key Change by order line
|  |  | Manage Ship To related Integration Setup |  | *Create and Update Ship To Details *Create/Modify Address *View Shipping / Billing Address *View Delivery Address | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
|  | ? | Price List | EBS price list LOV
|  |  | Item | Item LOV
|  |  | Synchronize Parts\Products | Synchronize the EBS PIM Products and BOM information with CPQ
|  |  | Synchronize BOMs | Synchronize the EBS PIM Products information with Sales Cloud
|  | ? | Order Details view | Order details view
|  | Data Load\Conversion | Parts Information | Part Conversion: Sync existing and new item\parts
|  | Integration | BOM Sync | Sync any new changes to BOM
|  |  | PriceBook | PriceBook
|  |  | EDI Orders | This integration process includes quote creation, adding product, other required quoting option, validations and order processing
|  |  | Customer Lookup | Get Customer Details
|  |  | Quote\Line Item Sync | Upsert Quote\Line Item attributes
|  |  | Export Attachment | Export quote related documents\attachments
|  |  | Import Attachment | Import quote related documents\attachments
|  |  | Quote\Line to Opportunity\Revenue Lines Sync | Synch primary quote\line details to Opportunity\Revenue Lines Sync
|  |  | TAX Integration | Process required to calcuate TAX for finance team
|  |  | Credit Card Processing | Process required to capture Credit Card details
|  | Service | Item Availability | Item/Warehouse Availibility. ML has functionality. Plan is to replicate for CPQ call.
|  | Service | Address Infomarion | Bill To/Ship To/Deliver To Address. Return address type by Account Id
|  | Service | Sales Order Details | Sales order additional information
|  | API | Create EBS Order | Quote to Order API for converting CPQ quote to order
|  | API | Update EBS Order | Order update initiated from CPQ. Updates will depend on matrix
|  | API | Cancel EBS Order\Order Lines Setups | Order cancellation API executed from CPQ |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
| ? | API | BOM Exists | Checks if inbound configuration from CPQ exists as BOM in EBS
| ? | API | Create BOM | Creates BOM in EBS from inbound CPQ configuration
| ? | Service | Copy End User ID | Copies line end user to line attribute
|  | Service | Validate End User | End user validation call
|  | Service | Item Supply/Demand | Returns item supply and demand for an item in all orgs
|  | Service | Item On Hand Quantity | Returns onhand quantity for item in all orgs
|  | Service | Calculate Item Weight | Calculate iem weight of configured items (components)
|  | Service | Load item attributes | Fetches and sets various item attributes on order line
|  | Service | Get ATO flag | Derives if item is ATO item or stock item
|  | Transaction | Update Item Weight | Update MLC UOM cross reference item data
|  | Service | Assign Serial Number | Gets next available serial number for a model
|  | Service | Validate Key Master | Master validation entered on order line or in configuration
|  | Service | Validate Serial Number | Combination key serial number validation
|  | Service | Validate Control Key | Validates control key for model
|  | Service | Get Existing Control Key | Gets list of control keys used by end user
|  | Service | Validate ADA Serial Number | Validates serial number for ADA lock
|  | Service | Get ADA Master Key Availability | Query to determine available master key for ADA locker locks
|  | Service | Get Next ADA Bind Code/Serial | Reviews registration to return next blind code/serial for ADA lock
|  | Service | Get KD Begin Master Key | Retrieve beginning key for KD order
|  | Service | Check Serial Quantity | Checks key serial quantity against ordered quantity
|  | Service | Validate System | Validates key configuration - item, key range Id, end user…
|  | Service | Assign Door Key | Assigns master and change key for residential door hardware
|  | Integration | Order Header Sync | Sync order header updates from EBS to CPQ
|  | Integration | Order Line Sync | Sync order line updates from EBS to CPQ
|  | Service | Line Set | Order line level "Line Set" option list
|  | Service | Get Item Availability Date | Returns date for order line value
|  | Service | Get Set Availability Date | Calculates and returns order line Item Available Date
|  | Service | Set ship sets | Determines ship sets at order line level. Part of custom booking process.
|  | Service | Sales Rep Search | Sales Rep list of values
|  | Service | Additional Order \Lne Information related setup | Display order header information (standard functionality) |  | 20 | 20 | 100 | 15 | 20 | 175 | 4.375
|  | Service | Expedite | Custom information request displaying various line item details (complex) |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  | Service | Calculate Order Weight | Custom calculation of order weight |  | 3.2 | 3.2 | 16 | 2.4 | 3.2 | 28 | 0.7
|  | Service | View Adjustments Header\Line Integration Setups | View adjustments applied at order header level; Adjustment, Reason tabs |  | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  | Service | View Charges (Line) Integration Setup | View charges applied to order line level | *Prepare Payload\Parameters *Validate and Parse response *Error Handling | 4.8 | 4.8 | 24 | 3.6 | 4.8 | 42 | 1.05
|  | Service | Get Default Sales Rep | Derives default sales rep populated on order header
|  | Service | Get Sales Channel | Get default sales channel based on order type
|  | Service | Get Ship To Attributes | Get DFF values based on ship to
|  | Service | Get Standard Order Information | Standard items populated by Oracle during order creation
|  | Service | Duplicate Order Check | Checks if order is duplicate base on customer, ship to, attribute13 and date range
|  | Service | Customer Pre-Set Notes | Automated notes added to order based on customer
|  | Service | Set Line Attributes | Enables and disables order line fields based on item, item type, item attributes
|  | Service | Validate Set Size | Validation of quantity ordered set value
|  | Service | Validate Order Quantity | Validates ordered quantity against customer rounding code and item attributes
|  | Service | Copy Attribute Field | Updates order line attriubute field with new value if different
|  | Service | Validate Order Line | Validates if customer item cross reference is needed and available
|  | Service | Set Request Date | Calculates Request Date, Promise Date and Schedule Ship Date on order line
|  | Service | MLC Insert Update Valiate | Calls Validate Line, verifies ship set values
|  | Service | Validate Line | Verifies is all required data has been defined on the order line
| Pricing | API | Price Request Integration Setup | Wrapper package around Oracle Price Request API |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
| Pricing | Data Load | Oracle Price Lists | EBS price list integration to CPQ
| Pricing | Data Load | Promotions List | EBS promotion list integration to CPQ
| Pricing | Data Load | Price Override Users | Users with access to override prices based on EBS profile
| Pricing | Integration | Price Promotions Sync | Sync promotion updates from EBS to CPQ
| Pricing | Integration | Price Override Users | Sync users with pricing override access to CPQ
| Pricing | Integraton | Price List Sync | Sync price list updates from EBS to CPQ
| Pricing | Service | View Tax Details | View taxes applied at order line level
[11 empty] | 882 | 22.05
[11 empty] | 0 | 0
[11 empty] | 0 | 0
| Other Activities |  | Cut Over & Migration |  |  | 4 | 4 | 20 | 3 | 4 | 35 | 0.875
|  |  | SIT |  |  | 8 | 8 | 40 | 6 | 8 | 70 | 1.75
|  |  | UAT |  |  | 4 | 4 | 20 | 3 | 4 | 35 | 0.875
|  |  | Change Mangement |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | PMO |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | HyperCare |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Detailed Technical Documentation |  |  | 16 | 16 | 80 | 12 | 16 | 140 | 3.5
|  |  | Knowledge Transfer |  |  | 12 | 12 | 60 | 9 | 12 | 105 | 2.625
[11 empty] | 805 | 20.125
| Grand Total | [9 empty] | 13900.25 | 347.5063
[9 empty] | Developers | Months
[9 empty] | 5 | 17.3753
Months by Functional Area
[9 empty] | Sales Cloud - CPQ Integration | 7.7
[9 empty] | Service Cloud - CPQ Integration | 3.5
[9 empty] | Product Catalog & Configuration | 26.8953
[9 empty] | General Setup | 17.0625
[9 empty] | Bid Management | 0
[9 empty] | Channel Partner | 0
OE Activities
Integration Impact
[9 empty] | Total | 55.1578